## InstructionsForUse
This event planning tool was developed by Krista Jensen at York University's Knowledge Mobilization Unit and is distributed with permission. The information contained in this template is for demonstration purposes only. You will have to customize the activities and timelines for completion according to the requirements of your event.
Instructions for use:
- Customize the information in the title (row 1) and the activities or "work to be done" (column C)to what needs to be done for your event
- Note the initials for the person(s) responsible for completing each task in (column E)
- Fill in the timeline for completion of activities (column D). Consider the event date as "week zero (0)" and work backwards from it.
- Type "a" to insert a checkmark in (column B) to mark an item as completed.
If you have questions or need support for planning your KT event please contact the KT Core www.neurodevnet.ca/kt

## Faculty Expo
Project Name: Knowledge Mobilization Expo 2010 Project Schedule
Activity | Done | Work to be Done | Due | Who | Notes
Registration | a | Send out "Hold the date" message | Week 08 | AS
|  | Compile list of potential invitees | Week 08 | KEJ
|  | Draft invite | Week 08 | KEJ
|  | Draft registration form | Week 06 | KEJ
|  | Set-up online registration on Eventbrite | Week 09 | KEJ
|  | Send out general invite | Week 06 | KEJ
|  | Send out invite to Faculty and Grad student Listserv | Week 06 | KEJ
|  | Post announcement on blog and in newsletter | Week 05 | KEJ
|  | Optional follow up invite | Week 04 | KEJ | Depending on response
|  | Send out final agenda and directions via email | Week 03 | KEJ
|  | Tweet weekly about event | Week 09-0 | KEJ | use #KMbExpo2011
|  | Track registration | Week 03-0 | KEJ
|  | Registration on the day of event | Week 0 | students
Facilities |  | Book room | Week 10
|  | Site visit | Week 04 | MJ, AS, KEJ
|  | Book catering | Week 06 | KEJ
|  | Book microphones | Week 06 | AM
|  | Book projectors for break out session | Week 06 | AM
|  | Book audio speakers | Week 06 | AM
|  | Bring external computer speakers | Week 0
|  | Bring travel kit | Week 0 |  | extension cord, duct tape
Morning Plenary 1 Speakers |  | Confirm Stan for welcome address | Week 09 | MJ
|  | Invite speakers | Week 08 | DP, MJ
John T
Discussion panellist
|  | Get thank-you gifts for speakers | Week 0 |  | York pen, usb, stickies, mints
|  | Ask for speakers notes and/or ppt presentations and bios | Week 01
Morning Plenary 2 Speakers |  | Confirm facilitator | Week 07
|  | Invite speakers | Week 08 | MJ
Janice C
Valerie R
|  | Get thank-you gifts for speakers | Week 01 |  | York pen, usb, stickies, mints
|  | Ask for speakers notes and/or ppt presentations and bios | Week 01
Closing speaker |  | Confirm Stan | Week 08 | MJ
|  | Invite speakers | Week 07
Danielle Z
Break out sessions |  | Invite session speakers/panelists | Week 08 | MJ
#1 Research 101
Mina S
#2 KMb 101
|  | Michael J |  | MJ
#3 Social Media
Brent M
|  | Decide who will introduce each session | Week 09
|  | Get thank-you gifts for facilitators | Week 01 |  | York pen, usb, stickies, mints
Community Booths |  | Decide which 7 orgs to invite | Week 08 | MJ, AS, KEJ | CBERN, Venture lab, Living in YR, Blue Door, TEIDI, Food network, ResearchImpact
|  | Invite organizations to display | Week 08
|  | Arrange for tables in classroom for display | Week 06 | AM
|  | Develop passport | Week 06 | MJ, AS, KEJ
|  | Booth passport prize | Week 01
Materials |  | Draft registration packages including:
|  | Maps to venues including public transit directions | Week 04
|  | Agendas | Week 04
|  | Write Full Program including description of break-out sessions | Week 04
|  | Develop evaluation forms | Week 01
|  | Get 100 red research folders | Week 01
|  | Name tags | Week 01
|  | List of all confirmed attendees | Week 01 |  | Add #KMbExpo to all materials and ppts
|  | Posters and banners | Week 0
|  | Brochures | Week 01
|  | Signage | Week 01
|  | Passports | Week 06 | AS
|  | Box for passports | Week 0 | AS, KEJ
|  | Speaker bios | Week 01
|  | Travel kit | Week 0 | MJ
|  | Plastic candy bowl | Week 0 | KEJ
|  | Camera | Week 0
|  | Candy | Week 0
|  | Pens and paper | Week 0 | KEJ
|  | Load speakers ppt presentations on key or disc | Week 0
Communications |  | Post 1st Expo registration announcement on blog and in newsletter | Week 08 | AS
|  | Post 2nd Expo registration announcement on blog and in newsletter | Week 04 | KJ
|  | Arrange to have event recorded by ABEL | Week 06 | KJ | record morning session and closing speech
|  | Send out map and reminder to all registered attendees | Week 0
|  | Post in YorkU events | Week 04
|  | Blog posting | Week 0
|  | Post speaker presentations and speaking notes on slideshare (email KT Core) | Week -1
|  | Post ABEL videos on RI site and O3 | Week -1
Note on B2: CNS: to make a check mark- make sure font is set to Marlett and type a
Note on B4: Krista Jensen: Type in the letter a to make a check mark

## Community Expo
Project Name: Knowledge Mobilization Expo 2010 Project Schedule
Activity | Done | Work to be Done | Due | Who | Notes
Registration |  | Send out "Hold the date" message | Week 18 | KJ
|  | Compile list of potential invitees | Week 11 | KJ
|  | Draft invite | Week 13 | GM
|  | Draft registration form | Week 13 | GM
|  | Set-up online registration | Week 13 | KJ
|  | Invite main invitees (both internal and external) | Week 12 | KJ
|  | Send out general invite | Week 08 | KJ
|  | Post announcement on blog and in newsletter | Week 08 | KJ
|  | Send out registration package via email | Week 03 | KJ
|  | Send out registration package to Ros | Week 03 | KJ
|  | Send out registration package to Faculty Listserv | Week 03 | KJ
|  | Track registration | Week 03-0 | KJ
Facilities |  | Search for potential sites | Week 21 | KJ
|  | Visit Le Parc and decide on rooms | Week 19 | KJ, MJ, GM
|  | Get quote from Beryl | Week 19 | KJ
|  | Send $1000 for deposit | Week 18 | KJ
|  | Finalize menu for the day | Week 02 | KJ, MJ, GM
|  | Visit to confirm set up | Week 01 | KJ, MJ, GM
|  | Order AV equipment | Week 6 | KJ
|  | Confirm AV equipment | Week 02 | KJ
|  | Set up Internet for afternoon plenary | Week 04 | KJ
Morning Plenary Speakers |  | Confirm David D for welcome address | Week 02
|  | Invite speakers | Week 18
Morning plenary
|  | Sandra C |  | DP
|  | Jeniffer C |  | DP
|  | Get thank-you gifts for speakers | Week 01 | KJ
|  | Ask for speakers notes and/or ppt presentations and bios | Week 01 | KJ
Break out session |  | Decide on format and speakers for 3 sessions | Week 18 | KJ, MJ, DP
|  | Invite session speakers/panelists | Week 18 | KJ, MJ
#1 Producer Push
Matthew S
Andrei S
#2 User Pull
#3 Co-Production
Stewart D
Karen K
Mobilizing Minds
|  | Decide who will introduce each session | Week 18 | all
|  | Get thank-you gifts for facilitators | Week 01 | KJ
Breaks with video displays |  | Look into cost of renting monitors | Week 19 | KJ
|  | Notify project folks about video display |  | KJ
|  | Confirm who will be presenting videos | Week 4 | KJ
Michaela H
Steve G
Isolde D
Geoff W
Tanya G
|  | Book monitors for videos | Week 6 | KJ
Afternoon Plenary |  | Invite speakers | Week 18
|  | Afternoon plenary | Week 18
|  | CIHR |  | DP
|  | VP NSERC |  | DP
|  | SSHRC |  | DP
|  | McConnell Foundation |  | DP
|  | Provinicial funder |  | DP
|  | Get thank-you gifts for speakers | Week 01 | KJ
|  | Ask for speakers notes and/or ppt presentations and bios | Week 01 | KJ
Unconference Time |  | Purchase large Post-it notes and markers | Week 01 | KJ
|  | Make up table number cards | Week 01 | KJ
Closing speaker |  | Invite Daniele | Week 18 | KJ
|  | Get thank-you gifts for speakers | Week 01 | KJ
Materials |  | Draft registration packages including:
|  | Maps to venues including public transit directions | Week 04 | GM
|  | Agendas | Week 04 | GM
|  | Write Full Program including description of break-out sessions | Week 04 | KJ
|  | Develop evaluation forms | Week 03 | GM
|  | Get 100 red research folders | Week 01 | KJ
|  | Name tags | Week 02 | GM
|  | List of all confirmed attendees | Week 01 | GM
|  | Posters and banners | Week 01 | KJ
|  | Brochures | Week 01 | KJ
|  | Signage | Week 01 | KJ
|  | Speaker bios | Week 01 | KJ
Allyson M
Lynda W
Peter L
Heidi S
Jennifer M
Brent M
Andrei S
Jackeline B
|  | Load speakers ppt presentations on key or disc | Week 0 | KJ
Communications |  | Post 1st Expo registration announcement on blog and in newsletter | Week 11 | KJ
|  | Post 2nd Expo registration announcement on blog and in newsletter | Week 5 | KJ
|  | Arrange to have event recorded by ABEL | Week 11 | KJ
|  | Send out map and reminder to all registered attendees | Week 1 | KJ
|  | Y-file story announcing upcoming event | Week 04 | KJ
|  | Y-file story covering event | Week 0 | KJ
|  | Y-file story after event | Week -1 | KJ
|  | Blog posting | Week 0 | KJ
|  | Post speaker presentations and speaking notes on slideshare (contact KT Core) | Week -1 | KJ
|  | Post ABEL videos on RI site and O3 | Week -1 | KJ
Note on B2: CNS: to make a check mark- make sure font is set to Marlett and type a

## Expo timelines
Due | Done | Work to be Done | Who | Notes
|  | Notify project folks about video display | KJ
|  | Confirm who will be presenting videos | KJ
Week 21 | a | Search for potential sites | KJ | Booked Le Parc
Week 19 |  | Visit Le Parc and decide on rooms | KJ, MJ, GM | Last year we had rooms 5 and 6
Week 19 |  | Get quote from Beryl | KJ
Week 19 | a | Look into cost of renting monitors | KJ
Week 18 |  | Send out "Hold the date" message | KJ | Post hold the date message for inclusion in Oct enewsletter
Week 18 |  | Send $1000 for deposit | KJ
Week 18 |  | Invite speakers
Week 18 |  | Afternoon plenary
Week 18 |  | Decide on format and speakers for 3 sessions | KJ, MJ, DP | mtg Oct 22 to discuss
Week 18 |  | Invite session speakers/panelists | KJ, MJ
Week 13 |  | Draft invite | GM | Can just update last year's
Week 13 |  | Draft registration form | GM | Can just update last year's
Week 13 |  | Set-up online registration | KJ
Week 12 |  | Invite main invitees (both internal and external) | KJ
Week 12 |  | Order AV equipment | KJ | last year we used Oortworks Corp and the large meeting package, 2 6' screens and 1 wireless mic w/ stand- this year get 1 more wireless mic and maybe monitor to show videos on
Week 11 |  | Compile list of potential invitees | KJ | Last year's attendees plus
Week 10 |  | Holidays
Week 09 |  | Holidays
Week 08 |  | Send out general invite | KJ | Limit of 2 attendees per org
Week 08 |  | Post announcement on blog and in newsletter | KJ
Week 08 |  | Post Expo registration announcement on blog and in newsletter | KJ
Week 04 |  | Maps to venues including public transit directions | GM
Week 04 |  | Agendas | GM
Week 04 |  | Write Full Program including description of break-out sessions | KJ
Week 04 |  | Arrange to have event recorded by ABEL | KJ
Week 04 |  | Y-file story announcing upcoming event | KJ
Week 03-0 |  | Track registration | KJ
Week 03 |  | Send out registration package via email | KJ | Including detailed info about sessions and location
Week 03 |  | Send out registration package to Ros | KJ
Week 03 |  | Send out registration package to Faculty Listserv | KJ
Week 03 |  | Develop evaluation forms | GM
Week 02 |  | Finalize menu for the day | KJ, MJ, GM
Week 02 |  | Confirm AV equipment | KJ
Week 02 |  | Confirm David D for welcome address
Week 02 |  | Buy backer boards for posters | KJ
Week 02 |  | Name tags | GM
Week 01 |  | Visit to confirm set up | KJ, MJ, GM
Week 01 |  | Get thank-you gifts for speakers | KJ
Week 01 |  | Ask for speakers notes and/or ppt presentations and bios | KJ
Week 01 |  | Get thank-you gifts for facilitators | KJ
Week 01 |  | Purchase large Post-it notes and markers | KJ
Week 01 |  | Make up table number cards | KJ
Week 01 |  | Get 100 red research folders | KJ
Week 01 |  | List of all confirmed attendees | GM
Week 01 |  | Posters and banners | KJ
Week 01 |  | Brochures | KJ
Week 01 |  | Signage | KJ
Week 0 |  | Load speakers ppt presentations on key or disc | KJ
Week 0 |  | Y-file story covering event | KJ
Week 0 |  | Blog posting | KJ
Week -1 |  | Y-file story after event | KJ
Week -1 |  | Post speaker presentations and speaking notes on RI site and O3 | KJ
Week -1 |  | Post ABEL videos on RI site and O3 | KJ
Note on B1: CNS: to make a check mark- make sure font is set to Marlett and type a